## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL EfFECTIVE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #7 | 8 | Alessandra, Lorenzo, Sonia, Martina
Create the DB |  | Alessandra, Lorenzo, Sonia, Martina |  | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the table in DB for the activities |  | Lorenzo, Martina |  | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Alessandra, Sonia |  | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement web page's logic |  | Lorenzo, Martina |  | 4 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Testing phase |  | Alessandra, Sonia |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
User Story #16 | 2 | Lorenzo, Martina
Update the DB associating a specific type to each activity |  | Lorenzo, Martina |  | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3 | 8 | Alessandra, Lorenzo, Sonia, Martina
Update the DB associating the information to each activity |  |  |  | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Lorenzo, Martina |  | 5 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0
Implement web page's logic |  | Alessandra, Sonia |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
Testing phase |  | Lorenzo, Martina |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
User Story #4 | 5 | Alessandra, Lorenzo, Sonia, Martina
Update the database inserting the SMP file in PDF format of the selected activity |  | Alessandra, Martina |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement the logic showing SMP file in PDF format of the selected activity |  | Sonia, Lorenzo |  | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
User Story #5 | 2 | Alessandra, Lorenzo, Sonia, Martina
Update the DB adding for each activity the workspace notes |  | Lorenzo, Martina |  | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add a text area to the web page |  | Alessandra, Lorenzo |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
Implement text area's logic |  | Alessandra, Lorenzo, Sonia, Martina |  | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
Implement the logic showing the current workspace notes of the selected activity |  | Sonia, Martina |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
ESTIMATED TOTAL |  |  |  | 40.25 | 5 | 7.75 | 4 | 3 | 4 | 7.5 | 3 | 2 | 3 | 1 | 0
ACTUAL PARTIAL |  |  |  |  | 40.25 | 35.25 | 27.5 | 23.5 | 20.5 | 16.5 | 9 | 6 | 4 | 1 | 0
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #7 | 8 | Alessandra, Lorenzo, Sonia, Martina
Create the DB |  | Alessandra, Lorenzo, Sonia, Martina |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the table in DB for the activities |  | Lorenzo, Martina |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Alessandra, Sonia |  | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement web page's logic |  | Lorenzo, Martina |  | 6 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Testing phase |  | Alessandra, Sonia |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0
User Story #16 | 2 | Lorenzo, Martina
Update the DB associating a specific type to each activity |  | Lorenzo, Martina |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3 | 8 | Alessandra, Lorenzo, Sonia, Martina
Update the DB associating the information to each activity |  |  |  | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Lorenzo, Martina |  | 4 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0
Implement web page's logic |  | Alessandra, Sonia |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Testing phase |  | Lorenzo, Martina |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1
User Story #4 | 5 | Alessandra, Lorenzo, Sonia, Martina
Update the database inserting the SMP file in PDF format of the selected activity |  | Alessandra, Martina |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement the logic showing SMP file in PDF format of the selected activity |  | Sonia, Lorenzo |  | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
User Story #5 | 2 | Alessandra, Lorenzo, Sonia, Martina
Update the DB adding for each activity the workspace notes |  | Lorenzo, Martina |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add a text area to the web page |  | Alessandra, Lorenzo |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
Implement text area's logic |  | Alessandra, Lorenzo, Sonia, Martina |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
Implement the logic showing the current workspace notes of the selected activity |  | Sonia, Martina |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
ESTIMATED TOTAL |  |  |  | 37 | 7 | 7 | 2 | 5 | 5 | 2 | 1 | 3 | 4 | 1 | 0
ACTUAL PARTIAL |  |  |  |  | 37 | 30 | 23 | 21 | 16 | 11 | 9 | 8 | 5 | 1 | 0

## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 59.5 | 59 | 41 | 20 | 18 | 14