## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #9 | 8 | Alessandra, Lorenzo, Sonia, Martina
Create the table in DB for the maintainers and their skills |  |  |  | 1
Create the web page (GUI) |  |  |  | 6
Implement web page's logic |  |  |  | 8
Testing phase |  |  |  | 3
User Story #8 | 5 | Alessandra, Lorenzo, Sonia, Martina
Implement the logic to view the skills of each maintainer |  |  |  | 5
User Story #10 | 7 | Alessandra, Lorenzo, Sonia, Martina
Update the table in DB for the maintainers adding their availability |  |  |  | 1
Implement the logic to select the day in which the maintainer is available |  |  |  | 3
User Story #2 | 5 | Alessandra, Lorenzo, Sonia, Martina
Create the web page (GUI) |  |  |  | 3
Implement web page's logic |  |  |  | 3
Testing phase |  |  |  | 3
User Story #11 | 3 | Alessandra, Lorenzo, Sonia, Martina
Implement the logic to select the slot of availability time |  |  |  | 3
User Story #12 | 8 | Alessandra, Lorenzo, Sonia, Martina
Implement the logic to send a notification to the selected Maintainer profile with a copy by e-mail to the Production manager |  |  |  | 7
Testing phase |  |  |  | 2
TOTAL |  |  |  | 43

## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 59.5 | 59 | 41 | 20 | 18 | 14