## Agile Product Backlog
AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  | Sprint 1 | [7 empty] | 25
1 | User Story #7 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-11-23 | 2020-12-01 | Yes | Yes | High | Complete | 8 | Yes | This section is for the drop-down list
2 | User Story #16 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-11-24 | 2020-11-24 | Yes | Yes | High | Complete | 2 | Yes | Yes | High | Complete
3 | User Story #3 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-11-24 | 2020-11-03 | Yes | Yes | High | Complete | 8 | Yes | No | Medium | In Progress
4 | User Story #4 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-11-24 | 2020-11-28 | Yes | Yes | Medium | Complete | 5 | Yes |  | Low | Not Started
5 | User Story #5 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-11-24 | 2020-11-29 | Yes | Yes | Medium | Complete | 2 | Yes
Sprint 2
6 | User Story #9 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-12-04 | 2020-12-07 | Yes | Yes | High | Complete | 8 | Yes
7 | User Story #8 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-12-11 | 2020-12-12 | Yes | Yes | High | Complete | 5 | Yes
8 | User Story #10 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-12-04 | 2020-12-13 | Yes | Yes | Medium | Complete | 7 | Yes
9 | User Story #2 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-12-11 | 2020-12-12 | Yes | Yes | High | Complete | 5 | Yes
10 | User Story #11 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-12-07 | 2020-12-10 | Yes | Yes | High | Complete | 3 | Yes
11 | User Story #12 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-12-11 | 2020-12-13 | Yes | Yes | Medium | Complete | 8 | Yes
12 | User Story #1 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-12-06 | 2020-12-11 | Yes | Yes | Low | Complete | 5 | No
13 | User Story #13 | " " | Alessandra, Lorenzo, Sonia, Martina | 2020-12-10 | 2020-12-13 | Yes | Yes | High | Complete | 8 | No