## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL EFFECTIVE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #9 | 8 | Alessandra, Lorenzo, Sonia, Martina
Update the DB for the maintainers and their skills |  | Alessandra, Martina |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Sonia, Lorenzo |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement web page's logic back-end |  | Lorenzo, Sonia |  | 5.5 | 2.5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement web page's logic front-end |  | Alessandra, Martina |  | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing phase |  | Martina, Sonia, Alessandra, Lorenzo |  | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
User Story #8 | 5 | Alessandra, Lorenzo, Sonia, Martina
Create the web page (GUI) |  | Sonia, Alessandra |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0
Implement the logic to view the skills of each maintainer |  | Lorenzo, Martina |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
Testing phase |  | Martina, Sonia, Alessandra, Lorenzo |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
User Story #10 | 7 | Alessandra, Lorenzo, Sonia, Martina
Update the table in DB for the maintainers adding their availability |  | Alessandra, Lorenzo |  | 1.5 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement the logic to select the day in which the maintainer is available |  | Sonia, Martina |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing phase |  | Martina, Sonia, Alessandra, Lorenzo |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
User Story #2 | 5 | Alessandra, Lorenzo, Sonia, Martina
Create the web page (GUI) |  | Alessandra, Martina |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Implement web page's logic |  | Sonia, Lorenzo |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
User Story #11 | 3 | Alessandra, Lorenzo, Sonia, Martina
Update the DB for the maintainers' working hours |  | Sonia, Alessandra |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Lorenzo, Martina |  | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
Implement the logic to select the slot of availability time |  | Alessandra, Lorenzo, Sonia, Martina |  | 5 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0
Testing phase |  | Martina, Sonia |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
User Story #1 | 5 | Alessandra, Lorenzo, Sonia, Martina
Update the DB in order to manage users |  | Alessandra, Sonia |  | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Martina, Sonia |  | 2 | 0 | 0 | 0 | 0.5 | 1.5 | 0 | 0 | 0 | 0 | 0
Implement web page's logic |  | Martina, Lorenzo |  | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0
Testing phase |  | Alessandra, Lorenzo |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
User Story #12 | 8 | Alessandra, Lorenzo, Sonia, Martina
Implement the logic to send a notification to the selected Maintainer profile with a copy by e-mail to the Production manager |  | Alessandra, Lorenzo, Sonia, Martina |  | 12 | 0 | 2 | 1 | 1 | 1.5 | 1.5 | 2 | 1 | 1 | 1
User Story #13 | 8 | Alessandra, Lorenzo, Sonia, Martina
Update the DB in order to manage EWO |  | Sonia, Martina |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
Create the web page (GUI) |  | Alessandra, Lorenzo |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0.5
Implement the logic in order to modify activity's information specific to the EWO |  | Alessandra, Lorenzo, Sonia, Martina |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
Testing phase |  | Sonia, Martina |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
ESTIMATED TOTAL |  |  |  | 70.5 | 6.5 | 6 | 6.5 | 7.5 | 7 | 4.5 | 7 | 9 | 8 | 8.5 | 0
ACTUAL PARTIAL |  |  |  |  | 70.5 | 64 | 58 | 51.5 | 44 | 37 | 32.5 | 25.5 | 16.5 | 8.5 | 0
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #9 | 8 | Alessandra, Lorenzo, Sonia, Martina
Update the DB for the maintainers and their skills |  | Lorenzo, Martina |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Sonia, Alessandra |  | 6 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement web page's logic back-end |  | Alessandra,Martina |  | 6 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Implement web page's logic front-end |  | Lorenzo, Sonia |  | 6 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Testing phase |  | Martina, Sonia, Alessandra, Lorenzo |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
User Story #8 | 5 | Lorenzo, Martina
Create the web page (GUI) |  | Sonia, Alessandra |  | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Implement the logic to view the skills of each maintainer |  | Lorenzo, Martina |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Testing phase |  | Martina, Sonia, Alessandra, Lorenzo |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
User Story #10 | 7 | Alessandra, Lorenzo, Sonia, Martina
Update the table in DB for the maintainers adding their availability |  | Alessandra, Sonia |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement the logic to select the day in which the maintainer is available |  | Lorenzo, Martina |  | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0
Testing phase |  | Martina, Sonia, Alessandra, Lorenzo |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
User Story #2 | 5 | Alessandra, Lorenzo, Sonia, Martina
Create the web page (GUI) |  | Alessandra, Martina |  | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0
Implement web page's logic |  | Sonia, Lorenzo |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
User Story #11 | 3 | Alessandra, Lorenzo, Sonia, Martina
Update the DB for the maintainers' working hours |  | Sonia, Alessandra |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Lorenzo, Martina |  | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
Implement the logic to select the slot of availability time |  | Alessandra, Lorenzo, Sonia, Martina |  | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
Testing phase |  | Martina, Sonia |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
User Story #1 | 5 | Alessandra, Lorenzo, Sonia, Martina
Update the DB in order to manage users |  | Alessandra, Sonia |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Martina, Sonia |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Implement web page's logic |  | Martina, Lorenzo |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Testing phase |  | Alessandra, Lorenzo |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
User Story #12 | 8 | Alessandra, Lorenzo, Sonia, Martina
Implement the logic to send a notification to the selected Maintainer profile with a copy by e-mail to the Production manager |  | Alessandra, Lorenzo, Sonia, Martina |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
User Story #13 | 8 | Alessandra, Lorenzo, Sonia, Martina
Update the DB in order to manage EWO |  | Sonia, Martina |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the web page (GUI) |  | Alessandra, Lorenzo |  | 5 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0
Implement the logic in order to modify activity's information specific to the EWO |  | Alessandra, Lorenzo, Sonia, Martina |  | 5 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0
Testing phase |  | Sonia, Martina |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
ESTIMATED TOTAL |  |  |  | 72 | 5 | 6 | 7 | 8 | 8 | 10 | 9 | 7 | 7 | 5 | 0
ACTUAL PARTIAL |  |  |  |  | 72 | 67 | 61 | 54 | 46 | 38 | 28 | 19 | 12 | 5 | 0

## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 59.5 | 59 | 41 | 20 | 18 | 14